| INCIDENT RESPONSE GUIDE Mission: To safely manage the operations of the nursing home during response to internal flooding and system restoration. |  |
| --- | --- |
| DIRECTIONS |  |
|  | Read this entire response guide and review Incident Management Team Chart. |
|  | Use this response guide as a checklist to ensure all tasks are addressed and completed. |
| OBJECTIVES |  |
|  | Prevent or minimize impact of nursing home flooding. |
|  | Ensure safe resident care and medical management. |
|  | Communicate situation to staff, residents, media, community officials, and regulatory agencies. |
|  | Evacuate the nursing home (partial or complete) as required. |
| IMMEDIATE ACTIONS (OPERATIONAL PERIOD 0-2 HOURS) |  |
|  | COMMAND |
|  | (Incident Commander): Activate the Nursing Home Emergency Operations. Activate Command Staff and Section Chiefs, as appropriate. Establish operational period and incident objectives; develop the Incident. Notify local emergency management and regulatory agencies of situation and immediate actions. Communicate with other health care facilities to determine: - Situation Status - Surge Capacity - Resident transfer/bed availability - Ability to loan needed equipment, supplies, medications, personnel, etc. Inform staff, residents, and families of situation and actions underway to prevent/limit flooding. Prepare media staging area. Conduct regular media briefings, in collaboration with the local Emergency Operations Center/Joint Information Center. (Safety Officer): Conduct safety assessment of low-lying flooded areas and assess risks and impacts to residents, staff, and families. NOTE: Section duties and responsibilities remain the responsibility of the Incident Commander unless delegated. |

| IMMEDIATE ACTIONS (OPERATIONAL PERIOD 0-2 HOURS) |  |
| --- | --- |
|  | Operations |
|  | Activate the nursing home’s internal (or external) flooding plan. Ensure continuation of resident care and essential services. Consider partial or complete evacuation of the nursing home or relocation of residents and services into safe areas of the nursing home. Ensure the operations of alternate power supplies (i.e., back-up generators). Maintain communications systems; activate alternate/redundant communications systems as needed. Evaluate the flooded area(s) and identify safety issues. Institute measures to prevent flooding and protect nursing home resources, as appropriate. Secure the nursing home and limit access and egress. Implement business continuity planning and protection of resident records. Assess nursing home damage and projected impact of rising flood waters on the nursing home. |
|  | Planning |
|  | Establish operational period and incident objectives; develop the Incident Action Plan in collaboration with the Incident Commander. Gather and validate situational information and projected impact. Implement resident and staff tracking, as appropriate. |
|  | Logistics |
|  | Maintain utilities and activate alternate systems as needed. Investigate and provide recommendations for auxiliary power (battery powered lights, etc.). Provide for water, food, and rest periods for staff. Obtain supplies to maintain function of emergency generators (fuel, parts, etc.). Obtain supplemental staffing, as needed. Prepare for transportation of evacuated residents. Validate and/or activate the back-up communications systems. |

| INTERMEDIATE (OPERATIONAL PERIOD 2-12 HOURS) |  |
| --- | --- |
|  | COMMAND |
|  | Establish a resident information center to notify resident families of situation and resident locations. Notify local emergency management, emergency operations center, and regulatory agencies of situation status, critical needs, and plans for evacuation, if appropriate. |
|  | Operations |
|  | Continue essential resident care management. Initiate clean-up operations, as appropriate. Reassess need for, or prepare for, evacuation. Continue to maintain utilities. Provide mental health support to residents and families as needed. Continue to secure the nursing home, including unsafe areas. Activate business continuity plans, including protection of records and possible relocation of business functions. Continue to evaluate nursing home integrity and safety of flooded areas. Initiate clean-up, as appropriate. |
|  | Planning |
|  | Continue resident and personnel tracking, as needed. Update and revise the Incident Action Plan and distribute to Command Staff and Section Chiefs. |
|  | LOGISTICS |
|  | Provide additional staffing and resources as required. |
|  | Finance/Administration |
|  | Track cost expenditures and estimate cost of nursing home damage and lost revenue. Initiate documentation of any injuries or nursing home damage. Facilitate the procurement of supplies, equipment, medications, and contracting for nursing home clean up or repair. |

| EXTENDED (OPERATIONAL PERIOD BEYOND 12 HOURS) |  |
| --- | --- |
|  | COMMAND |
|  | (Incident Commander): Update and revise the Incident Action Plan and prepare for demobilization. Continue to update internal leaders on the situation status. Continue with briefings and situation updates with staff, residents, and families. Continue resident information center operations. Continue to notify local emergency operations center and regulatory agencies of situation status. Continue resident information center operations in collaboration with Public Information Officer. (Safety Officer): Continue to evaluate flooded areas and nursing home integrity for safety, and take immediate corrective actions. |
|  | Operations |
|  | Continue essential resident care management and services. Continue to evaluate nursing home damage/integrity and initiate clean-up/repair activities. Continue repair and clean-up operations, as appropriate. Continue evacuation of the nursing home, if implemented. Ensure the transfer of residents’ belongings, medications, and records, when evacuated. Continue to maintain utilities. Continue to secure the nursing home, including unsafe areas. Continue business continuity activities and relocation of business services, if appropriate. Prepare for demobilization and system recovery. |
|  | Planning |
|  | Revise and update the Incident Action Plan. Initiate demobilization and system recovery plan. |
|  | Logistics |
|  | Provide supplemental staffing as needed. |
|  | Finance/Administration |
|  | Continue to track cost expenditures. Continue to facilitate contracting for nursing home repair and clean up. |

| DEMOBILIZATION/SYSTEM RECOVERY |  |
| --- | --- |
|  | COMMAND |
|  | (Incident Commander): Determine nursing home status and declare termination of the incident. Conduct final media briefing and assist with updating staff, residents, families, and others of the termination of the event. Communicate final nursing home status and termination of the incident to local emergency operations center, area facilities, officials, and regulatory agencies. Assist with the repatriation of transferred residents. (Safety Officer): Ensure nursing home safety and restoration of normal activities. Ensure nursing home repairs are completed in conjunction with the Operations and Logistics Sections. |
|  | Operations |
|  | Restore normal resident care operations. Ensure restoration of utilities and communications. Complete a nursing home damage report, progress of repairs, and estimated timelines for restoration of nursing home to pre-event condition. |
|  | Planning |
|  | Complete a summary of operations, status, and current census. Conduct after-action reviews and debriefings. Develop the after-action report and improvement plan for approval by the Incident Commander. |
|  | LOGISTICS |
|  | Restock supplies, equipment, medications, food, and water. Ensure communication and IT/IS operations return to normal. Provide stress management and mental health support to staff. |
|  | Finance/Administration |
|  | Compile a final report of response and nursing home repair costs for approval by the Incident Commander. Work with local, state, and federal emergency management to begin reimbursement procedures for cost expenditures related to the event. Contact the insurance carriers to assist in documentation of structural and infrastructure damage and initiate reimbursement and claims procedures. |

| DOCUMENTS AND TOOLS |  |
| --- | --- |
|  | Nursing Home Emergency Operations Plan |
|  | Nursing Home Evacuation Plan |
|  | Flood Response Plan |
|  | Utility Failure Plan |
|  | Nursing Home Business Continuity Plan |